## PM Audit Checklist
PM Quality Checklist
EQUIPMENT DESCRIPTION : |  | GRUGR#2 |  | EQUIPMENT CODE
PM DESCRIPTION : |  | PM Plan for GRUGR#2 |  | PM Type (Elect/Mech/ C&I) | Mech/Elect
AREA : |  | BO - 1 |  | SUB AREA | BO - 2
ENGINEER INCHARGE: |  | Afzal Khan ,Chinna. |  | INSPECTION BY: | Ulaganathan & CS Ravi
DATE: |  | 2022-02-27 |  | SHIFT | A
S.NO. | PM CHECKPOINTS |  | STATUS (Y/N/Part) | REMARKS / OBSERVATIONS | MARKS (MAX) | Marks Scored
1 | PM compliance for schedule and duration |  | Yes | PM schedule compliance ok | 5 | 5
2 | PM checklist/tasklist site availbility during PM |  | Yes | Available at site with PM engineer. | 5 | 4
3 | Is PM tasklist / SMP comprehensive, considering specfic measurable and check points |  | Yes | PM checklist OK and SMP revised to be done | 5 | 4
4 | PM checklist / tasklist field execution compliance, filled data - quality & actual duration |  | Partial | Hydraulic oil leakages attended in TT pusher during PM. Rest of the HPU leakages to be attended on oppurtunity basis and in PM | 20 | 15
5 | PM tasklist activity / process compliance as per SMP requirements & SMP availabilitty |  | Yes | Available. | 15 | 15
6 | PM manpower & technicians knowledge / competency for task list |  | Yes | Adequate and experienced for the job. | 10 | 10
7 | Engineer presence / supervion at work site during PM |  | Yes | Engineers available | 10 | 10
8 | Availability of tools & tackles as per PM tasklist |  | Yes | Available. | 5 | 5
9 | Availbility of required spares and consumables during PM |  | Yes | Available. | 5 | 5
10 | PM activity and observation not addressed due to manpower / time / spare / consumable |  | No | Manpower taking tea break for almost one hour. | 5 | 3
11 | Equipment related defects / observations availability and closure during PM |  | Yes | Need to log in more defects for improvement of PM effectiveness. Use of reg tagging and ZL notifications to be improved. | 5 | 2.5
12 | Abnormalities observed recorded, if not attended during the PM converted into MA |  | Partial | Corrections done in PM. | 5 | 5
13 | During & before PM closure, equipment related CLTI activities compliance |  | Partial | CLTI done. | 5 | 5
| PM Quality Score |  |  |  | 100 | 88.5
S.NO. | PM, Equipment and asset relateted specific observations (Man, Machine, Method, Materail, Execution etc.)
1 | PM was done on schedule, Proper supervision available during PM.
2 | Abnormalities found and corrective action taken during PM.
3 | Safety observations to be recorded so as to ease of maintenance.

## Sheet1
PM Quality Checklist
EQUIPMENT DESCRIPTION : |  |  | EQUIPMENT CODE
PM DESCRIPTION : |  |  | PM Type (Elect/Mech/ C&I)
AREA : |  |  | SUB AREA
ENGINEER INCHARGE: |  |  | INSPECTION BY:
DATE: |  |  | SHIFT
S.NO. | PM CHECKPOINTS | STATUS (Y/N/Part) | REMARKS / OBSERVATIONS | MARKS (MAX) | Marks Scored
1 | PM compliance for schedule and duration |  |  | 5
2 | PM checklist/tasklist site availbility during PM |  |  | 5
3 | Is PM tasklist / SMP comprehensive, considering specfic measurable and check points |  |  | 5
4 | PM checklist / tasklist field execution compliance, filled data - quality & actual duration |  |  | 20
5 | PM tasklist activity / process compliance as per SMP requirements & SMP availabilitty |  |  | 15
6 | PM manpower & technicians knowledge / competency for task list |  |  | 10
7 | Engineer presence / supervion at work site during PM |  |  | 10
8 | Availability of tools & tackles as per PM tasklist |  |  | 5
9 | Availbility of required spares and consumables during PM |  |  | 5
10 | PM activity and observation not addressed due to manpower / time / spare / consumable |  |  | 5
11 | Equipment related defects / observations availability and closure during PM |  |  | 5
12 | Abnormalities observed recorded, if not attended during the PM converted into MA |  |  | 5
13 | During & before PM closure, equipment related CLTI activities compliance |  |  | 5
| PM Quality Score |  |  | 100
S.NO. | PM, Equipment and asset relateted specific observations (Man, Machine, Method, Materail, Execution etc.)

## Sheet2
PM Quality Checklist
EQUIPMENT DESCRIPTION : | EQUIPMENT CODE
PM DESCRIPTION : | PM Type (Elect/Mech/ C&I)
AREA : | SUB AREA
ENGINEER INCHARGE: | INSPECTION BY:
DATE: | SHIFT